## Unit Test Plan
Unit Test Plan
Project | financial-research-ai | Owner | Charan Kummagiri | Timeline | Sep 16, 2026 – Oct 19, 2026; Latest Git: 2026-10-19
Test ID | Module | Test Scenario | Expected Result | Test Type | Status | Owner
UT-001 | ExtractionAgent | Parse currency-formatted financial values with commas and symbols ($1,250, Rs. 5,000, 500) | Currency symbols and separators are stripped and valid float value is returned. | Unit | Passed | Charan Kummagiri
UT-002 | ExtractionAgent | Handle missing or invalid metric values (e.g. non-numeric strings, empty text) | Missing values return None without raising unhandled exception. | Unit | Passed | Charan Kummagiri
UT-003 | ExtractionAgent | Calculate financial ratios with valid inputs and zero/null denominators | Ratios return correct percentages when valid; zero/null denominators return None without division error. | Unit | Passed | Charan Kummagiri
UT-004 | ExtractionAgent | Extract financial year from various formats (FY2025, Annual Report 2024, Form 10-K 2023) | Correct 4-digit financial year string is returned. | Unit | Passed | Charan Kummagiri
UT-005 | DocumentAgent | Reject empty, corrupt, or unreadable PDF files | Processing raises ValueError or FileNotFoundError with descriptive validation message. | Unit | Passed | Charan Kummagiri
UT-006 | DocumentAgent | Index valid annual report PDF into ChromaDB | PDF text is chunked, embedded via SentenceTransformers, and upserted into ChromaDB with metadata. | Integration | Passed | Charan Kummagiri
UT-007 | ComparisonAgent | Extract metrics across multi-chunk document (DEF-001 regression scenario) | All ordered chunks for a document are concatenated and passed to ExtractionAgent. | Unit / Regression | Failed (Pending Fix) | Charan Kummagiri
UT-008 | ResearchAgent | Query validation and classification (blank input, oversized prompt, valid finance query) | Blank/oversized queries rejected with appropriate warning; valid prompt categorized into analysis task. | Unit | Passed | Charan Kummagiri
UT-009 | RedFlagAgent | Evaluate financial risk triggers and distinguish boilerplate risk disclosures | Real risk indicators flagged with severity; generic forward-looking disclaimers not marked as red flags. | Unit | Passed | Charan Kummagiri
UT-010 | RedFlagAgent | Parse negative parenthesized numbers (500) and prefixed currency Rs. 500 | Values parsed correctly as negative floats (-500.0) without regex failure. | Unit | Passed | Charan Kummagiri
UT-011 | ReportAgent | Generate structured report combining metrics, red flags, and document citations | Report object contains executive summary, key metrics table, risk findings, and evidence sources. | Unit | Passed | Charan Kummagiri
UT-012 | ReportAgent | Generate downloadable PDF summary using ReportLab | Formatted PDF document is created in output directory with structured headings and tables. | Integration | Passed | Charan Kummagiri
UT-013 | Workflow (LangGraph) | Dynamic execution routing for single-document and multi-company analysis | Single document routes through extraction and red-flag nodes; multi-company routes through comparison node. | Integration | Passed | Charan Kummagiri
UT-014 | API (FastAPI) | Validate document upload constraints (session ID, file type, 50MB size limit) | Non-existent session, non-PDF file, or oversized payload returns expected 400/404 HTTP status code. | API / Integration | Passed | Charan Kummagiri
UT-015 | API (FastAPI) | Health check endpoint reports service status and LLM configuration | GET /health returns HTTP 200 with status=ok, llm_provider, and gemini_configured fields. | API | Passed | Charan Kummagiri
UT-016 | GeminiClient | Candidate model fallback upon quota exhaustion or transient error | When primary model fails with 429 or 404, fallback models are attempted sequentially. | Unit / Resilience | Passed | Charan Kummagiri
Notes | Test scenarios UT-001 through UT-016 cover core agent methods, API endpoints, and LangGraph workflow routing. UT-007 validates DEF-001 behavior and remains in Failed (Pending Fix) status until chunk concatenation is merged. Statuses reflect manual and direct module execution verification conducted on 2026-10-19.